Deployment Checklists

Reviewing Windows 95 Features

Task	Team	Start week	Duration

1:   Read Introducing Microsoft Windows 95 (available 	Executive,	Week 1	7 days

from Microsoft Press; ISBN 1-55615-860-2), or the 	Planning

Windows 95 Reviewer's Guide (available from WinNews

forums on the Internet and other online services).

2:   For information about business justifications for deploy-	Executive,	Week 1	14 days

ing Windows 95, review total cost of ownership, migra-	Planning

tion, and productivity studies published by analysts such

as Gartner Group, Inc. Use these studies to assess the

impact of Windows 95 on the bottom line of your business.

3:   Acquire additional copies of the Windows 95 Resource	Planning	Week 2	1 day

Kit for review during the deployment process.

Preparing the Teams

Task	Team	Start week	Duration

1:   Assign the project manager, if appropriate (usually this	Planning	Week 2	—

is the head of the Information Systems department).

2:   Select key Planning and Installation team members,  	Planning,	Week 2	5 days

if appropriate. Make sure to include an applications 	Installation

specialist for evaluating 32-bit applications.

3:   Acquire Windows 95 (the compact disc version is pre-	Planning	Week 2	1 day

ferred because it contains system administration tools).

4:   Identify your client and server hardware and software 	Planning	Week 3	5 days

configurations on the network.

5:   Set up a testing lab.	Planning	Week 2	1 day

6:   Acquire test computers for use as the network server 	Planning	Week 2	5 days

and clients. Choose computer models that are typical of

those used in your organization.

7:   Install the applications software and line-of-business	Planning	Week 3	3 days

tools in the lab to simulate the network environment. Also

identify the mission-critical and noncritical business and

other applications typically used in your organization.

Create a checklist for evaluating the compatibility and

performance of these applications during testing.

8:   To prepare for configuration planning, review detailed 	Planning,	Week 3	3 days

discussions of product features in the Windows 95  	Installation

Resource Kit; study Chapter 2, "Deployment Strategy

and Details," in the Resource Kit.

9:   To prepare for supporting Windows 95, study the 	Support	Week 3	10 days

entire Windows 95 Resource Kit. As an option, obtain

Windows 95 TrainCast instructional videotapes from

Microsoft. As another option, arrange for the team and

other individuals, as appropri-ate, to attend training at a

Microsoft Authorized Technical Education Center and

participate in the Microsoft Certified Professional program.

10: As an option, read Inside Windows 95 from Microsoft 	Planning,	Week 2	10 days

Press for technical details on the internal operation of 	Installation,

Windows 95.	Support

Performing the Lab Test

Task	Team	Start week	Duration

1:   Before running Windows 95 Setup, make sure that the 	Installation	Week 4	0.1 day

computer meets your company's standards and the

Windows 95 minimum standards for operation -- at

least a 4-MB 386DX or better. If not, perform the hard-

ware upgrades now.

2:   Defragment the hard disk and scan it for viruses. 	Installation	Week 4	0.1 day

3:   Back up and verify key data and configuration files, 	Installation	Week 4	0.1 day

such as INI, AUTOEXEC.BAT, and CONFIG.SYS

files. Also back up the Windows and DOS directories,

and all files in the root directory. Make a system

startup disk containing SYS.COM, COMMAND.COM,

and FDISK.EXE.

4:   Ensure that the current network client software is 	Installation	Week 4	1 day

functioning properly and, referring to the checklist of

inventoried applications, make sure that all important

applications operate correctly.

5:   Install Windows 95 on the test computer in the lab, 	Planning,	Week 4	1 day

using the preferred client configuration identified in the 	Installation

previous phase.

6:   Test the installation:	Planning,	Week 4	2 days

- Can you connect to and browse the network?	Installation

- Can you print both locally and across the network?

- Can you perform the core operations of each applica-

tion locally and on the network (including opening,

closing, and printing)?

- Can you shut down successfully?

7:  Optionally, if you have several test computers, 	Installation,	Week 5	2 days

compare your old client configuration under 	Planning

Windows 3.x and your new preferred configuration.

How do the two compare in terms of the following:

- Functionality for administering the computer?

- Performance for local disk and network actions?

- Ease of use for performing common tasks?

- Stability of the computer under stress?

- Compatibility with applications and hardware?

8:  If the specified client configuration did not work 	Planning,	Week 5	As required

as expected, modify and document the differences 	Installation

until a working preferred client configuration is

installed.

9:  Perform a complete restoration of operating system files 	Installation	Week 5	1 day

and system capabilities for your old client configuration

on the computer running Windows 95.

10: Evaluate the restoration process for problems. Docu-	Installation,	Week 5	0.5 day

ment the process and the modifications made.	Planning

11: Have all team members participate in installing the 	Installation,	Week 5	3 days

preferred configuration on a variety of hardware.	Planning

Planning the Pilot Rollout

Task	Team	Start week	Duration

1:   Use Server-based Setup to install Windows 95 source 	Planning,	Week 6	1 day

files on a server. Make setup choices based on your 	Installation

client configuration, including whether you will run a

shared copy of Windows 95 from the server, or run

Windows 95 locally on the client computer. Perform the

following steps:

- Set up the distribution server

- Set up the client from the network

See Chapter 4, "Server-Based Setup for Windows 95,"

in the Windows 95 Resource Kit for step-by-step

instructions. Document any changes to this process.

2:   Create and test an automated installation by creating a 	Planning,	Week 6	2 days

setup script to predefine settings for Setup. Document 	Installation

the key parts of the setup script that vary by installation.

3:   Determine and test how you will push the installation 	Planning,	Week 6	3 days

from the server without having to touch the client com-	Installation

puters. (See Chapter 5, "Custom, Automated, and Push

Installations," in the Windows 95 Resource Kit.)

Options:

- Modify login scripts on the server.

- Use system management software.

- Send a setup script (batch file) that runs Windows 95

Setup as an embedded link in an electronic mail message.

Document the process for the rest of the Installation team.

4:  Evaluate the Windows 95 installation process for oppor-	Planning,	Week 7	2 days

tunities to upgrade or improve your organization's exist- 	Executive

ing technology infrastructure. For example, a system man-

agement software tool can help you administer computers

on the network more easily, and it can help with the push

installation process.

5:  Document in checklist form the logistics of the pilot 	Installation,	Week 7	3 days

installation, such as the total time for installation, the 	Planning

new software or tools to be purchased, the group

selected as the pilot users, and the scheduling of specific

installations. Use this before the rollout to make sure you

are completely prepared. Document goals for the pilot roll-

out to be used as evaluation criteria for rating the success

of the rollout.

6:   Send a memo to your users to clearly explain how the 	Planning	Week 7	1 day

installation process will affect their daily work schedule

and describe the differences they will see after the install-

ation is completed.

7:  Develop a user training course (or hire a training vendor 	Planning,	Week 6	5 days

to prepare one). Use the Windows 95 Help and Intro-	Support,

ducing Microsoft Windows 95 (supplied with the 	Training

Windows 95 distribution disks) to "jump start" your

training efforts.

8:  Establish a support plan for the pilot user group. This 	Planning,	Week 7	5 days

includes the names and phone numbers of people to	Support

contact for assistance, a short list of the top questions

and answers, and troubleshooting tips.

9:   Set up the lab or classroom with computers for training.	Training	Week 7	2 days

10: Edit the Windows 95 Help file (if appropriate) to include 	Planning,	Week 8	4 days

any company-specific information. Repeat this after the	Support

pilot rollout is completed.

Conducting the Pilot Rollout

Task	Team	Start week	Duration

1:   Select a pilot user group that is willing and able 	Planning	Week 8	2 days

(particularly in terms of their workload) to handle the

installation process.

2:   Train the users.	Training	Week 8	5 days

3:   Back up the Windows and DOS directories and the 	Installation	Week 9	5 days

files on the root directory of the test computers.

4:   Following the logistics checklist prepared in the 	Installation	Week 9	10 days

previous phase, perform the installation in the same

manner that you expect to install Windows 95 through-

out the company. Compare your results against goals

and evaluation criteria (developed in the previous task)

for this process.

5:   Have your technicians on site for the initial installations 	Support	Week 9	15 days

to document the process and problems, and to support

the users. Have other technicians monitor time and all

measurable factors in the installation process. Record

these measurements for later evaluation.

6:   Ensure that all computers are "up and running" as 	Planning,	Week 11	3 days

expected. Make note of possible improvements to the 	Installation,

installation, training, or support, where appropriate.	Support

7:   Survey members of the pilot user group about their 	Planning	Week 12	3 days

satisfaction with the installation process and take feed-

back on what could have been done better.

8:   Continue to monitor the pilot installation for a week to 	Support,	Week 11	5 days

make sure that everything continues to run smoothly.	Planning

9:   Prepare a checklist of issues to resolve for the final roll-	Support,	Week 11	5 days

out. Include in this checklist the areas identified in step 6 	Planning

as needing improvement, comments from the user survey,

and the results of comparing your rollout goals and eval-

uation criteria against actual performance.

10: If the pilot program did not run smoothly or user feed-	Planning,	Week 12	See "Plan

back was poor, conduct additional pilot installations 	Installation	the Pilot

until the process works well. 		Rollout"

Finalize the Rollout Plan

Task	Team	Start week	Duration

1:  Determine your rollout goals — specifically the number 	Planning,	Week 12	5 days

of computers on which you will install Windows 95 and 	Executive

the time expected for completion. During preparation for

final rollout, check off items on this list as they are

resolved.

2:  Budget the resources, in terms of personnel and tools, 	Planning	Week 12	3 days

required to meet your goals.

3:  If necessary, present the budget and obtain approval 	Executive,	Week 13	2 days

for the resources and the rollout process.	Planning

4:  Hire and train the extended Installation team and	Training,	Week 13	10 days

purchase the additional software or tools needed.	Installation

5:  Update the company's hardware and software standards 	Planning	Week 13	2 days

lists.

6:  Update the company's policies and practices manuals 	Planning	Week 13	2 days

or guidelines for use of computers and the network.

7:  Notify your users that company standards and policies 	Planning	Week 13	1 day

for computer use will be enforced prior to the installation

and that they must bring their computers into compliance.

8:  If appropriate, edit the Windows 95 Help file to add 	Planning,	Week 14	3 days

company-specific Help for line-of-business applications.	Support

9:  For each computer, create a template as a database 	Installation	Week 13	2 days

for documenting and tracking any system problems

or deficiencies that require further attention.

10: Post the updated template to a central network location.	Installation	Week 13	2 days

Rolling Out Windows 95

Task	Team	Start week	Duration

1:   Set up the distribution servers by using Server-based 	Installation	Week 15	1 day

Setup and configuring the system policy files.

2:   Customize the server installation by adding or 	Installation	Week 15	2 days

removing the appropriate files, including the

MSBATCH.INF file.

3:   Notify the users of the upcoming installation.	Planning	Week 15	1 day

4:   Train the users on Windows 95.	Training	Week 16	As required

5:   If needed, upgrade the hardware on the client computers 	Installation	Week 16	As required

and remove any software not complying with company

policy.

6:  If needed, back up critical data and configuration files 	Installation	Week 16	As required

on the client computers.

7:   If needed, defragment the client hard disks.	Installation	Week 16	As required

8:   Optionally, you can temporarily reset the user password 	Planning	Week 17	As required

and ID for each computer, to allow your technicians

easy access to the client computer and to make sure that

the login scripts and environment operate correctly.

9:   Ensure that the client computers are fully operational 	Installation	Week 17	As required

and the real-mode network, if present, is running.

10: Prepare the client computers for the push installation 	Installation	Week 18	As required

process: edit the login scripts; run the management soft-

ware; or send the setup script, by electronic mail, to the

user.

11: Initiate the installation by having the user log on, 	Installation	Week 18	As required

double-click the setup script file, and so on.