PPPPPP     CCCCCC   PPPPPP    M     M                  P     P   C         P     P   MM   MM                  P     P   C         P     P   M M M M                  P     P   C         P     P   M  M  M                  PPPPPP    C         PPPPPP    M  M  M                  P         C         P         M     M                  P         C         P         M     M                  P         C         P         M     M                  P          CCCCCC   P         M     M PC PROJECT MANAGEMENT USER'S MANUAL   I.   INTRODUCTION        A.  PREPARATION          1.  The Node Network          2.  The Input Worksheet       B.  ENTERING THE BASE FILE       C.  SYSTEM GENERATED FILES       D.  CHANGING THE INPUT FILE   II. SYSTEM ERRORS  III.  OUTPUT       A.  Primary       B.  Cash Flow Analysis       C.  Barchart       D.  Current Cost Report       E.  Preceeder or Succeeder Display  IV.  APPENDIX       A.  Sample Input Form                            I.   INTRODUCTION  PCPM is  a  system of interactive programs for project management using the critical path  method.   The  system  is  designed  to  handle  all necessary functions internally or  allow the more sophisticated user to build and modify files on his/her own by making use of  system  editing software.  PCPM is menu-driven, that is, a menu of available options is displayed to  the  terminal  for the user to choose the desired option. When that particular function  has  been  completed,  PCPM  will  again display the menu. A.   PREPARATION      1.   The Node Network          To use PCPM the user must first have constructed a node network         representation of  the  project.   Each  activity  must  have a         description of up to 30 characters, a duration (time), and node         numbers.         The node network numbering must  be  performed  in  a  specific         fashion.  Each  node  is  assigned  an integer number from 1 to         1000 and nodes are numbered in ascending order with  the  first         node having  the  lowest  number  and  the last node having the         highest number.  The "from" node for each activity must be less         than (and not equal to) the "to" node for that activity.   Note         that not  all  numbers  between the start and finish have to be         used;  in fact, spacing  should  be  maintained  to  allow  for         future schedule changes.     2.   The Input Worksheet          Before input  at  the  terminal  is attempted, it is helpful to         make an input worksheet.  Enter the information from  the  node         network.  (See samples in the appendix).         Optional entries  for each activity are the report finish date,         percent complete, subcontractor name/code or other comment, and         activity cost.         Any report finish date entered must be "legal".  To be legal  a         date can  not fall on a weekend or holiday when working days is         the unit of time being used.  Also, a legal  date  can  not  be         prior to the start date of the project.         PCPM may  be run using any unit of time the user specifies.  It         is, however, up to the user to maintain consistency  of  input.         Examples of possibilites are:              Working days (does include weekends but not holidays).              Calendar days (does not include holidays).              Weeks (activity duration must be converted by the              user - e.g., 10 days duration should be entered as 2). B.   ENTERING THE BASE FILE      Using PCPM,  a  sample  input file can be created. Other functions,     including  creation of  a  holiday  file, critical  path  and  cash     flow analyses, and sorting output are also performed by using PCPM.     The user is guided interactively through each option of  the  menu.     After each option is complete, the system returns to the menu. C.   SYSTEM GENERATED FILES      Accessory files  to  the input file are created by the system based     upon the input file.  It is, therefore, important that this file be     accurately entered.  In general, the existence  of  system  created     files can  be  ignored  by  the  user.  They are merely cogs in the     machinery that allows PCPM to run.  The  following  information  is     included to satisfy the more curious users.     As options of the Main  Menu  are  performed,  the  system  creates     accessory files.  These accessory files are described with the base     file  name  and  a  three  letter  extension.   For  example,  when     utilizing OPTION 4 - CREATE/CHANGE  HOLIDAYS,  the  system  creates     (automatically) a file denoted by BASEFILENAME.HOL.     Here are  some  of the system created files for example file "LLP":         LLP/CFA   - output file for cash flow analysis         LLP/CPM   - input file for option 5 (main file)         LLP/CST   - output file for current cost report         LLP/DAY   - file of working vs. project days from Option 12         LLP/HOL   - file of holidays created by Option 3         LLP/LGS   - file of data for sorts used by Options 6,7,8, & 9         LLP/PRE   - output file containing predecessor printout         LLP/SRT   - sorted output file created by option 8         LLP/SUC   - output file containing successor printout         LLP/UPD   - updated input file created by Option 5 D.   CHANGING THE INPUT FILE      Changing the  input  file  is  easily   done   by   changing   node     connections, durations,  and/or  adding  report finish dates.  Once     the modifications to the input file are made, rerun Option 5.   The     system will quickly calculate the new durations, critical path, and     completion times.                     II.  IN CASE OF SYSTEM ERRORS      As many  error  traps  as  possible  have  been included to insure      efficient usage.  However, PCPM does not  check  every  item  each      time in order to keep processing time at a minimum.      If the  syStem  appears to  be "hung up", use the CTRL BREAK keys.      Enter the system again and check for unconnected nodes, or illegal      date usage.  The most common error is made  by  editing  the  data      files outside the PCPM system and leaving out commas or putting in      extra data.   The  simplest  solution is to perform editing within      the PCPM system.                              III.  OUTPUT      After exiting the PCPM system, output can be obtained by following      the directions for your printer.           A.  Primary Output               Primary output is a  list  of  all  activities  including               their estimated duration, actual duration (if completed),               early and  late start times, early and late finish times,               float, actual reported  finish  date,  and  subcontractor               name (or  any  comment)  associated  with  the  activity.               There is also a complete listing  of  all  critical  path               activities following  the  path(s)  from start to finish.               Primary output can be arranged in a variety of  sorts  by               utilizing Option 8.           B.  Cash Flow Analysis Output               This analysis projects monies  to  be  expended  on  each               activity during each month of the project.           C.  Bar Chart Output               PCPM outputs  a Gantt type bar chart showing the critical               path, float and activity duration using early start times               for each activity.           D.  Current Cost Report               This report shows total costs expended to date  for  each               activity based on percentage of project completion.           E.  Preceeder or Succeeder Display               This   report  shows  the  immediate   interrelationships               between activities - which activity immediately  preceeds               or succeeds  any  other activity as described by its from               and to nodes.                             IV.  APPENDIX                          A.  SAMPLE INPUT FORM       -----------------------------------------------------------                   FROM   TO   EST   REPORT  %  SUBCONTRACTOR ACT       DESCRIPTION NODE  NODE  TIME  FINISH  DUN  CODE (NAME) COST       -----------------------------------------------------------       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________       ___________________________________________________________

___________________________________________________________       ___________________________________________________________